## Schedule (2) (hidden)
Program: MWO | [204 empty] | Plan
Forecast
Freight
Manaus Manufacture | [204 empty] | Milestone
Project: MWO
[50 empty] | 2011 | [47 empty] | 2012 | [68 empty] | 2013 | [38 empty] | 2014
Revision 1: 2013, March, 13th | Month | Aug |  |  |  | Sept |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sept |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb
Task / Milestone | Week | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
CAR approval | Plan | [158 empty] | 1 | 1 | 1 | [48 empty] | 0
| Fcst | [158 empty] | 2 | 2 | 2 | [48 empty] | 0
PO for tooling (Cavity/Door), Assembly line and test equipment | Plan | [160 empty] | 4 | [48 empty] | 0
| Fcst | [160 empty] | 2 | [48 empty] | 0
Tooling lead Time - Cavity | Plan | [68 empty] | 1 | 1 | 1 | 1 | [89 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [42 empty] | 42
| Fcst | [161 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [41 empty] | 49
TRY OUT Cavity tools in China | Plan | [68 empty] | 1 | 1 | 1 | 1 | [95 empty] | 1 | 1 | [40 empty] | 14
| Fcst | [168 empty] | 2 | 2 | 2 | [38 empty] | 21
Cavity tooling - shipment by sea/customs | Plan | [93 empty] | 1 | [75 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [30 empty] | 70
| Fcst | [171 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [28 empty] | 70
TRY OUT Cavity tools in Brazil | Plan | [93 empty] | 1 | [85 empty] | 1 | 1 | [28 empty] | 14
| Fcst | [181 empty] | 2 | 2 | [26 empty] | 14
Tooling lead Time - Door | Plan | [78 empty] | 1 | [82 empty] | 1 | 1 | 1 | 1 | 1 | 1 | [42 empty] | 42
| Fcst | [159 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [37 empty] | 91
TRY OUT Door tools in China | Plan | [68 empty] | 1 | 1 | 1 | 1 | [95 empty] | 1 | 1 | [40 empty] | 14
| Fcst | [172 empty] | 2 | 2 | 2 | [34 empty] | 21
Assembly line and test equipment | Plan | [57 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [81 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [39 empty] | 56
| Fcst | [162 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [39 empty] | 56
TRY OUT Assembly line and test equipment | Plan | [57 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [87 empty] | 1 | 1 | [39 empty] | 14
| Fcst | [168 empty] | 2 | 2 | [39 empty] | 14
Assembly line and test equipment - shipment by air/customs | Plan | [93 empty] | 1 | [76 empty] | 3 | 3 | 3 | 3 | [35 empty] | 28 | Air freight
| Fcst | [170 empty] | 2 | 2 | 2 | 2 | [35 empty] | 28
INSTALLATION Assembly line and test equipment - Brazil | Plan | [93 empty] | 1 | [80 empty] | 1 | 1 | 1 | [32 empty] | 21
| Fcst | [174 empty] | 2 | 2 | 2 | [32 empty] | 21
| Plan | [93 empty] | 1 | [115 empty] | 0
| Fcst | [209 empty] | 0
PCB electronic board development | Plan | [93 empty] | 1 | [65 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [34 empty] | 112
| Fcst | [159 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [34 empty] | 112
Electronic tecnology transfer (considering similar PCB board) | Plan | [93 empty] | 1 | [68 empty] | 1 | 1 | [45 empty] | 14
| Fcst | [162 empty] | 2 | 2 | [45 empty] | 14
PCB Soldering process development and assembly line functional tests (Brazil) | Plan | [93 empty] | 1 | [71 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [35 empty] | 63
| Fcst | [165 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [35 empty] | 63
MCS Electronic board (China) | Plan | [93 empty] | 1 | [80 empty] | 1 | [34 empty] | 7
| Fcst | [174 empty] | 2 | [34 empty] | 7
MCS - China SKD - shipment by air | Plan | [93 empty] | 1 | [81 empty] | 3 | 3 | 3 | 3 | [30 empty] | 28
| Fcst | [175 empty] | 2 | 2 | 2 | 2 | [30 empty] | 28
MCS Electronic board (Brazil) | Plan | [93 empty] | 1 | [85 empty] | 1 | 1 | [28 empty] | 14
| Fcst | [179 empty] | 2 | 2 | [28 empty] | 14
PCB Solcering process reliability tests (external lab) | Plan | [93 empty] | 1 | [87 empty] | 1 | 1 | 1 | 1 | [24 empty] | 28
| Fcst | [181 empty] | 2 | 2 | 2 | 2 | [24 empty] | 28
| Plan | [93 empty] | 1 | [115 empty] | 0
| Fcst | [209 empty] | 0
Art work (Labels, Manual, etc) | Plan | [159 empty] | 1 | 1 | [48 empty] | 14
| Fcst | [159 empty] | 2 | 2 | [48 empty] | 14
BOM from China | Plan | [161 empty] | 1 | 1 | [46 empty] | 14
| Fcst | [161 empty] | 2 | 2 | [46 empty] | 14
BOM Brazil SAP | Plan | [163 empty] | 1 | 1 | [44 empty] | 14
| Fcst | [163 empty] | 2 | 2 | [44 empty] | 14
LI | Plan | [165 empty] | 1 | 1 | 1 | 1 | [40 empty] | 28
| Fcst | [165 empty] | 2 | 2 | 2 | 2 | [40 empty] | 28
| Plan | [209 empty] | 0
| Fcst | [209 empty] | 0
PO MCS/PR | Plan | [165 empty] | 4 | [43 empty] | 7
| Fcst | [165 empty] | 2 | [43 empty] | 7
MCS - China SKD - Cavity/Board - to certify Manaus Assembly line | Plan | [169 empty] | 1 | [39 empty] | 7
| Fcst | [173 empty] | 2 | [35 empty] | 7
MCS - China SKD - shipment by air | Plan | [170 empty] | 3 | 3 | 3 | 3 | [35 empty] | 28
| Fcst | [174 empty] | 2 | 2 | 2 | 2 | [31 empty] | 28
MCS - Brazil - Cavity/Board SKD - to certify Manaus Assembly line | Plan | [174 empty] | 1 | [34 empty] | 7
| Fcst | [178 empty] | 4 | [30 empty] | 7
MCS 2 - Brazil - Cavity/Board SKD - to certify Manaus Assembly line | Plan | [180 empty] | 2 | [28 empty] | 14
| Fcst | [180 empty] | 4 | [28 empty] | 7
Pilot Run - China SKD - Complete - to certify Manaus Assembly line | Plan | [170 empty] | 1 | [38 empty] | 7
| Fcst | [173 empty] | 2 | [35 empty] | 7
Pilot Run - China SKD - Complete - shipment by sea | Plan | [171 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [31 empty] | 49
| Fcst | [174 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [28 empty] | 49
Pilot Run - China SKD - Complete - Customs | Plan | [178 empty] | 1 | 1 | 1 | [28 empty] | 21
| Fcst | [181 empty] | 2 | 2 | 2 | [25 empty] | 21
Pilot Run - Brazil - Complete SKD - to certify Manaus Assembly line | Plan | [181 empty] | 1 | [27 empty] | 7
| Fcst | [184 empty] | 4 | [24 empty] | 7
| Plan | [209 empty] | 0
| Fcst | [209 empty] | 0
SUFRAMA Brazil manufacture auditing | Plan | [179 empty] | 1 | [29 empty] | 7
| Fcst | [174 empty] | 4 | [34 empty] | 7 | Linha pode ser auditada sem estar montado produto
SUFRAMA Brazil manufacture operation report | Plan | [174 empty] | 1 | 1 | [33 empty] | 14
| Fcst | [175 empty] | 2 | 2 | [32 empty] | 14
SUFRAMA Brazil manufature licence | Plan | [176 empty] | 1 | [32 empty] | 7
| Fcst | [177 empty] | 2 | 2 | 2 | [29 empty] | 21 | Se inmetro precisa 40 dias antes do embarque
INMETRO Brazil manufacture auditing/licence | Plan | [176 empty] | 1 | 1 | 1 | 1 | [29 empty] | 28
| Fcst | [177 empty] | 2 | 2 | 2 | 2 | [28 empty] | 28
| Plan | [209 empty] | 0
| Fcst | [209 empty] | 0
PO for China Mass Production | Plan | [177 empty] | 4 | [31 empty] | 7
| Fcst | [209 empty] | 0
Mass Production in China | Plan | [180 empty] | 1 | [28 empty] | 7
| Fcst | [180 empty] | 2 | [28 empty] | 14
Mass Production in China - shipment by sea | Plan | [181 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [21 empty] | 49
| Fcst | [181 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [21 empty] | 49
Mass Production in China - customs in Brazil (Manaus) | Plan | [188 empty] | 1 | 1 | 1 | [18 empty] | 21
| Fcst | [188 empty] | 2 | 2 | 2 | [18 empty] | 21
Mass Production in Brazil | Plan | [191 empty] | 4 | [17 empty] | 7
| Fcst | [191 empty] | 2 | [17 empty] | 7
| Plan | [209 empty] | 0
| Fcst | [209 empty] | 0
MCS - China Finish Good samples - samples for certification (performance and efficiency) | Plan | [169 empty] | 1 | [39 empty] | 7
| Fcst | [175 empty] | 2 | [33 empty] | 7
MCS - China Finish Good samples - shipment by air | Plan | [170 empty] | 1 | 1 | 1 | 1 | [35 empty] | 28
| Fcst | [176 empty] | 2 | 2 | 2 | [30 empty] | 21
| Plan | [209 empty] | 0
| Fcst | [209 empty] | 0
| Plan | [209 empty] | 0
| Fcst | [209 empty] | 0
| Plan | [209 empty] | 0
| Fcst | [209 empty] | 0
| Plan | [209 empty] | 0
| Fcst | [209 empty] | 0
| Plan | [209 empty] | 0
| Fcst | [209 empty] | 0
| Plan | [209 empty] | 0
| Fcst | [209 empty] | 0
MWO - China Milestones | Plan | [68 empty] | 1 | 1 | 1 | 1 | [94 empty] | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 4 | [6 empty] | 4
| Fcst | [175 empty] | 2 | [6 empty] | 2
Assembly line Tryout
Cavity tryout
Door tryout
[177 empty] | MCS & PR | [6 empty] | Mass Prod.
MWO - Brazil Milestones | Plan | [93 empty] | 4 | [50 empty] | 4 | [15 empty] | 4 | [16 empty] | 4 |  |  | 4 |  | 4 |  |  |  | 4 | [6 empty] | 4
| Fcst | [160 empty] | 2 | [16 empty] | 2 |  |  | 2 |  | 2 |  |  |  | 2 | [6 empty] | 2
[146 empty] | TPQRB | [15 empty] | PO tool & Assembly line | [16 empty] | MP PO
[182 empty] | MCS#1 Mns | [5 empty] | Pilot R. | [6 empty] | Mass Prod.
[184 empty] | MCS#2 Mns |  |  |  | Mns | [6 empty] | Mns

## Cronograma Físico - PORTARIA 2
ANEXO IV
PORTO DE IMBITUBA S.A.
CRONOGRAMA FÍSICO E FINANCEIRO
SERVIÇOS: AQUISIÇÃO DE 04 CONTAINERS DE 40 PÉS, SENDO 02 PARA ESTOQUE DOS EQUIPAMENTOS DE SSMA E 02 PARA BASE DA NEPOM / POLÍCIA FEDERAL NO PORTO ORGANIZADO DE IMBITUBA/SC
Tarefas |  | mês | 2017-05-01 | [5 empty] | 2017-06-01 | [5 empty] | 2017-07-01 | [5 empty] | 2017-08-01 | [5 empty] | 2017-09-01 | [5 empty] | 2017-10-01 | [5 empty] | 2017-11-01 | [5 empty] | 2017-12-01
[10 empty] | 20 |  |  | 21 | 22 | 23 | 24 |  |  | 25 | 26 | 27 | 28 |  | 29 | 30 | 31 | 32 |  |  | 33 | 34 | 35 | 36 | 37 |  |  | 38 | 39 | 40 | 41 |  | 42 | 43 | 44 | 45 | 46
|  | dias | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
|  | dia |  | 2017-05-15 | 2017-05-22 |  |  | 2017-05-29 | 2017-06-05 | 2017-06-12 |  |  | 2017-06-19 | 2017-06-26 | 2017-07-03 | 2017-07-10 |  |  | 2017-07-17 | 2017-07-24 | 2017-08-01 | 2017-08-07 |  | 2017-08-14 | 2017-08-21 | 2017-08-28 | 2017-09-04 |  |  | 2017-09-11 | 2017-09-18 | 2017-09-25 | 2017-10-02 | 2017-10-09 |  |  | 2017-10-16 | 2017-10-23 | 2017-11-01 | 2017-11-06 |  | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-11-01 | 2017-11-06 |  | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-11-01 | 2017-11-06 |  | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-11-01 | 2017-11-06 |  | 2017-11-13 | 2017-11-20 | 2017-11-27
Etapa 1 | Assinatura do contrato (empresa A) |  | 4
Etapa 2 | Documentação para entrada no Porto (empresa A) |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
2.1 | Entrega da documentação da equipe para acesso e integração |  |  | 1 | 1 | 1 | 1 | 1
2.2 | Integração dos funcionários no Porto de Imbituba | [7 empty] | 1 | 1 | 1 | 1 | 1 | 1
Etapa 4 | Início da obra | [13 empty] | 4
4.1 | Aquisição dos containers | [13 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
4.1.1 | Aquisição dos containers | [13 empty] | 1 | 1 | 1 | 1 | 1 | 1
4.1.2 | Adaptação dos containers conforme projeto anexo
4.1.3 | Recebimento dos containers prontos para montagem
4.1.4 | Montagem dos containers sobre bases já edificadas
4.2 | LIMPEZA GERAL
4.2.1 | LIMPEZA FINAL DA OBRA
4.2.2 | PAGAMENTO EM PARCELA ÚNICA
Liberação da área (pronta para uso)
Liberação das áreas (pronta para uso)
Legenda:
[10 empty] | 2 |  |  | duração das etapas principais
[10 empty] | 1 |  |  | duração dos serviços de cada etapa
[10 empty] | 4 |  |  | marcos principais
[10 empty] | 3 |  |  | marcos secundários
Note on F9: Rebecca: emissão O.S. - PULTRUDADOS
Note on L9: Rebecca: emissão OS - PAVIMENTO E OBRAS
Note on P9: Rebecca: início execução PISO // 1ª etapa
Note on V9: Rebecca: início da execução - PULTRUDADOS
Note on X9: Rebecca: emissão O.S. - RESINA
Note on Z9: Rebecca: conclusão execução PISO // 1ª etapa
Note on AA9: Rebecca: conclusão - PULTRUDADOS
Note on AB9: Rebecca: início execução PISO // 2ª etapa
Note on AM9: Rebecca: conclusão execução PISO // 2ª etapa

## Backup (hidden)
| Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul |  | Aug |  |  |  | Sept |  |  |  | Oct |  |  | Nov | Dec
DESIGN phase 2
CONSUMER RESEARCH
FINAL DESIGN
TESTE NOVA PLAT. 20, 25, 30 (eff) -DHL/TNT (CANOAS)
TESTE NOVA PLAT. 20, 25, 30 (pç cotação fornecedores) (Mns)
TESTE NOVA PLAT. 20, 25, 30 (certificação) FORMAL
APRESENTAÇÃO CAR
APROVAÇÃO CAR
TOOLING (metalico - Cavity) | [10 empty] | CN
TOOLING (plastico)
PO for Assembly line (Line and test equipment)
Assembly line and test equipment
TRY OUT Assembly line and test equipment
TRY OUT Cavity tools in China
TRY OUT Door in China
Art work (Labels, Manual, etc)
BOM from China
BOM Brazil SAP
LI
PO MCS/PR
MCS CHINA KIT (SKD - Cavity/Board) - Assembly line certification
MCS CHINA FG (Finish Good samples for certification)
MCS Shippemt by air
PR CHINA KIT (igual final)
TRANSPORTE KIT PR CHINA BR
LI placa elétrica
ENVIO CERTIFICAÇÃO (Energy/Efficiency certification by Brazil)
CERTIFICAÇÃO (Energy/Efficiency certification by Brazil)
TOOLING TRANSPORTE (CHINA - BR) Cavity
Assembly line shippment (CHINA - BR)
TRY OUT MANAUS
MCS MANAUS
PO MP
MASS PRODUCTION CN
SKD MATERIAL (CHINA - BR) | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PILOT RUN BR
VISTORIA SUFRAMA
LAUDO DE OPERAÇÃO
LI SUFRAMA
LI INMETRO
MASS PRODUCTION BR
LAUDO DE PRODUÇÃO
We are here

## Plan2 (hidden)
Visita a célula de montagem da placa eletrônica
Plano de qualificação da solda dos componentes
Tempo de resposta para modificações da placa (componentes)
Suporte EPS do prato
Infraestrutura de TI (criar centro MWO para Manaus)

## Plan1 (hidden)
Neptune Purifier Schedule A (RISKY) | April | May | Jun | July | Aug | Sept | Oct | Nov | Dec
Functional Prototype
Tooling | bar: May to July
Certification | bar: July to Oct
PO | bar: Sept
Production | bar: Sept to Oct
Field Test | bar: Sept to Oct
Shipment | bar: Sept to Nov
1st lot Mkt Launch | bar: Dec
Feb
Neptune Purifier Schedule B (safe) | April | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan
Functional Prototype | bar: April
Tooling | bar: May to July
Certification | bar: July to Oct
PO | bar: Nov
Production | bar: Nov to Dec
Field Test | bar: Oct to Dec
Shipment | bar: Nov to Jan
1st lot Mkt Launch
Neptune WD Schedule | April | May | Jun | July | Aug | Sept | Oct | Nov | Dec
3d design adaptation | bar: April
Functional Prototype | bar: May
Tooling | bar: May to July
Certification | bar: July to Aug
PO | bar: Sept
Production | bar: Sept to Oct
Field Test | bar: July to Sept
Shipment | bar: Sept to Nov
1st lot Mkt Launch | bar: Dec
Electric WD Schedule | April | May | Jun | July | Aug | Sept | Oct | Nov | Dec
Artwork | bar: April
Certification | bar: April to May
PO | bar: Jun
Production | bar: Jun to July
Field Test | bar: April to Jun
Shipment | bar: Jun to Aug
1st lot Mkt Launch | bar: Sept
[11 empty] | Feb | March
Neptune Purifier Schedule C (china) | April | May | Jun | July | Aug | Sept | Oct | Nov | Dec | Jan
Functional Prototype | bar: April to May
Tooling | bar: Jun to Aug
Certification | bar: Aug to Nov
PO | bar: Dec
Production | bar: Dec to Jan
Field Test | bar: Nov to Jan
Shipment | bar: Dec to Jan
1st lot Mkt Launch